## Summary
Test Plan Summary — Curriculum Tracker 2026–2027
Generated: 2026-06-04 ¦ App: curriculum-tracker-five.vercel.app ¦ Branch: main
Role | Test Suite | Total Cases | P0 | P1 | P2
Platform Admin | Authentication | 4 | 1 | 3 | 0
| Schools | 8 | 3 | 5 | 0
| Curricula | 13 | 9 | 2 | 2
| API Security | 3 | 0 | 3 | 0
School Admin | Authentication | 3 | 2 | 1 | 0
| Manage Users | 4 | 0 | 3 | 1
| School Setup — Subjects | 3 | 0 | 2 | 1
| School Setup — Grade Levels | 2 | 0 | 2 | 0
| School Setup — Standard Sets | 13 | 8 | 5 | 0
| School Setup — Class Assignments | 4 | 0 | 2 | 2
Teacher / HOD | Authentication | 3 | 1 | 2 | 0
| Standards Loading | 3 | 2 | 1 | 0
| My Units | 2 | 0 | 2 | 0
| Long Term Plans | 7 | 2 | 4 | 1
| Standards Coverage | 2 | 0 | 2 | 0
| Student Progress | 1 | 0 | 1 | 0
| HOD — Review | 8 | 5 | 3 | 0
| Regression | 3 | 1 | 2 | 0
| HOD — Analytics | 6 | 2 | 3 | 1
| HOD — Coaching | 11 | 2 | 6 | 3
| Interventions | 10 | 2 | 6 | 2
| Department Collaboration | 10 | 3 | 6 | 1
| Initiatives | 5 | 0 | 3 | 2
| Regression (new cases) | 2 | 1 | 1 | 0
| School Setup — Initiatives | 3 | 1 | 2 | 0
TOTAL |  | 133 | 45 | 72 | 16
Priority Key
P0 — Critical (test before any deploy)
P1 — Important (test in each cycle)
P2 — Nice to have (regression/edge cases)

## Platform Admin
Test Plan — Platform Admin ¦ Curriculum Tracker 2026–2027
Role: Platform Admin ¦ Total cases: 28 ¦ Generated: 2026-06-04
ID | Suite | Test Case | Preconditions | Steps | Expected Result | Priority | Status | Notes
PA-AUTH-01 | Authentication | Login as platform admin | Account zain.platform exists | 1. Go to app URL 2. Enter username: zain.platform 3. Enter password 4. Click Sign in | Lands on Schools page. Sidebar shows Schools and Curricula nav items only. | P0 | ⬜ Untested
PA-AUTH-02 | Authentication | Platform admin cannot access school admin routes | Logged in as zain.platform | 1. Call POST /api/admin/create-standard-set with platform admin token | Returns 403 Forbidden | P1 | ⬜ Untested
PA-AUTH-03 | Authentication | Platform admin cannot access teacher routes | Logged in as zain.platform | 1. Call GET /api/admin/list-users with platform admin token | Returns 403 Forbidden | P1 | ⬜ Untested
PA-AUTH-04 | Authentication | Sign out | Logged in as zain.platform | 1. Click Sign out in sidebar footer | Returns to login screen. Session cleared. | P1 | ⬜ Untested
PA-SCH-01 | Schools | Schools page loads | Logged in as zain.platform | 1. Click Schools in sidebar | Page title = 'Schools'. Table shows all schools with Name, City, Curriculum, Users, Created, Status columns. No tab switcher visible. | P0 | ⬜ Untested
PA-SCH-02 | Schools | Search schools by name | Multiple schools exist | 1. Type school name in search box | Table filters live. Non-matching schools hidden. | P1 | ⬜ Untested
PA-SCH-03 | Schools | Search schools by city | Schools with different cities exist | 1. Type a city name in search box | Table filters to matching city only. | P1 | ⬜ Untested
PA-SCH-04 | Schools | Create new school | Logged in as zain.platform | 1. Click New School 2. Fill name, city, country, curriculum type 3. Click Create | School appears in list. Active status badge shown. | P1 | ⬜ Untested
PA-SCH-05 | Schools | View school detail sheet | At least one school exists | 1. Click any school row | Detail sheet slides in showing school info and user count. | P1 | ⬜ Untested
PA-SCH-06 | Schools | Suspend a school — confirmation required | Active school exists | 1. Click ⋯ on a school → Suspend 2. Observe modal 3. Type wrong name 4. Try to confirm | Modal opens with school name. Confirm button disabled until exact name typed. | P0 | ⬜ Untested
PA-SCH-07 | Schools | Suspend school — confirm | Active school exists | 1. Click ⋯ → Suspend 2. Type exact school name 3. Click Suspend | School status changes to Suspended. Users at that school see suspended message. | P0 | ⬜ Untested
PA-SCH-08 | Schools | Unsuspend a school | Suspended school exists | 1. Click ⋯ → Unsuspend | School status changes to Active immediately. | P1 | ⬜ Untested
PA-CUR-01 | Curricula | Navigate to Curricula page | Logged in as zain.platform | 1. Click Curricula in sidebar | Full page navigation. Title = 'Curricula'. Separate from Schools page — no shared state. | P0 | ⬜ Untested
PA-CUR-02 | Curricula | Curricula list loads | Platform standard sets exist in DB | 1. On Curricula page | All platform standard sets shown. Each row shows name and subject/grade labels. | P0 | ⬜ Untested
PA-CUR-03 | Curricula | Empty state | No standard sets in DB | 1. Navigate to Curricula page | BookOpen icon + 'No curricula yet' message with New Curriculum button. | P2 | ⬜ Untested
PA-CUR-04 | Curricula | Create new curriculum — validation | On Curricula page | 1. Click New Curriculum 2. Leave Name empty 3. Attempt to click Create | Create button disabled while name is empty. | P0 | ⬜ Untested
PA-CUR-05 | Curricula | Create new curriculum | On Curricula page | 1. Click New Curriculum 2. Enter Name: 'NYSED Grade 9 ELA' 3. Subject label: 'English' 4. Grade label: 'Grade 9' 5. Click Create | New row appears in list with correct name and labels. Form closes. | P0 | ⬜ Untested
PA-CUR-06 | Curricula | Expand curriculum row | At least one curriculum with standards | 1. Click row or chevron to expand | Standards table appears below row. Table has Code, Strand, Description, delete columns. | P1 | ⬜ Untested
PA-CUR-07 | Curricula | Add standard — Strand is shadcn Select | Curriculum row expanded | 1. Click Add Standard 2. Observe Strand field | Strand field uses shadcn Select component (not native <select>). Dropdown shows RL, RI, W, SL, L. | P0 | ⬜ Untested
PA-CUR-08 | Curricula | Add standard to curriculum | Curriculum expanded, Add Standard form open | 1. Enter Code: 'RL.9.1' 2. Select Strand: RL 3. Enter Description 4. Click Add | Standard appears in table sorted by code. Form resets. | P0 | ⬜ Untested
PA-CUR-09 | Curricula | Delete standard from curriculum | Curriculum has at least one standard | 1. Click trash icon on a standard row | Standard removed immediately. No confirmation needed. | P1 | ⬜ Untested
PA-CUR-10 | Curricula | Delete curriculum — modal appears | At least one curriculum exists | 1. Click trash icon on curriculum row header | Confirmation modal opens. Shows curriculum name, warns about cascading delete of standards and school assignments. | P0 | ⬜ Untested
PA-CUR-11 | Curricula | Delete curriculum — cancel | Delete modal open | 1. Click Cancel in modal | Modal closes. Curriculum remains in list unchanged. | P0 | ⬜ Untested
PA-CUR-12 | Curricula | Delete curriculum — confirm | Delete modal open | 1. Click Delete in modal | Curriculum removed from list. Any schools assigned to it lose the assignment. | P0 | ⬜ Untested
PA-CUR-13 | Curricula | Collapsed row does not show standards count | Curriculum exists with standards | 1. View collapsed curriculum row | Row shows name and labels only. Standards are visible after expansion. | P2 | ⬜ Untested
PA-SEC-01 | API Security | Only platform_admin can create curricula | School admin token available | 1. POST /api/platform/curricula with school admin token | Returns 403 Forbidden | P1 | ⬜ Untested
PA-SEC-02 | API Security | Only platform_admin can delete curricula | Teacher token available | 1. DELETE /api/platform/curricula with teacher token | Returns 403 Forbidden | P1 | ⬜ Untested
PA-SEC-03 | API Security | Only platform_admin can add standards | School admin token available | 1. POST /api/platform/curricula/standards with school admin token | Returns 403 Forbidden | P1 | ⬜ Untested

## School Admin
Test Plan — School Admin ¦ Curriculum Tracker 2026–2027
Role: School Admin ¦ Total cases: 32 ¦ Generated: 2026-06-04
ID | Suite | Test Case | Preconditions | Steps | Expected Result | Priority | Status | Notes
AD-AUTH-01 | Authentication | Login as school admin | Account zain.admin exists | 1. Enter username: zain.admin 2. Enter password 3. Click Sign in | Lands on Manage Users page. Sidebar shows admin nav items (Manage Users, School Setup, Platform Settings, Curriculum Audit). | P0 | ⬜ Untested
AD-AUTH-02 | Authentication | Admin cannot access platform routes | Logged in as zain.admin | 1. POST /api/platform/curricula with admin token | Returns 403 Forbidden | P1 | ⬜ Untested
AD-AUTH-03 | Authentication | Admin cannot access other school data | Two schools exist | 1. GET /api/admin/school-curricula with School A admin token | Only returns School A's curriculum assignments. School B data not visible. | P0 | ⬜ Untested
AD-USR-01 | Manage Users | View users list | Logged in as zain.admin | 1. Click Manage Users | Table shows all users with username, role badge, joined date. | P1 | ⬜ Untested
AD-USR-02 | Manage Users | Add teacher user | On Manage Users | 1. Click Add User 2. Set role: Teacher 3. Fill username and password 4. Click Save | New teacher appears in list with Teacher badge. | P1 | ⬜ Untested
AD-USR-03 | Manage Users | Add HOD user | On Manage Users | 1. Click Add User 2. Set role: HOD 3. Fill details 4. Save | New HOD appears with HOD badge. | P1 | ⬜ Untested
AD-USR-04 | Manage Users | Filter users by role | Multiple users with different roles | 1. Change role filter dropdown | List filters to selected role only. | P2 | ⬜ Untested
AD-SUB-01 | School Setup — Subjects | View subjects | On School Setup | 1. Click School Setup → Subjects tab | All school subjects listed with colour badges. | P1 | ⬜ Untested
AD-SUB-02 | School Setup — Subjects | Add subject | On Subjects tab | 1. Click + Add Subject 2. Enter name 3. Save | Subject appears with auto-assigned colour slot. | P1 | ⬜ Untested
AD-SUB-03 | School Setup — Subjects | Delete subject | At least one subject exists | 1. Click trash on a subject | Subject removed from list. | P2 | ⬜ Untested
AD-GRD-01 | School Setup — Grade Levels | View grade levels | On School Setup | 1. Click Grade Levels tab | All grade levels listed in sort order. | P1 | ⬜ Untested
AD-GRD-02 | School Setup — Grade Levels | Add grade level | On Grade Levels tab | 1. Click + Add Grade Level 2. Enter name: 'Grade 9' 3. Save | Grade 9 appears in list. | P1 | ⬜ Untested
AD-STD-01 | School Setup — Standard Sets | Navigate to Standard Sets tab | School has subjects and grade levels | 1. School Setup → Standard Sets tab | Page shows Subject and Grade Level dropdowns. Description reads 'Select a subject and grade level, then choose the platform curriculum that applies.' | P0 | ⬜ Untested
AD-STD-02 | School Setup — Standard Sets | Select subject and grade — no assignment | No curriculum assigned for this combo | 1. Select a subject 2. Select a grade level | Shows 'No curriculum assigned' message. Search input and full platform library list visible. | P0 | ⬜ Untested
AD-STD-03 | School Setup — Standard Sets | Library shows all platform curricula | Multiple platform curricula exist | 1. Subject and grade selected, unassigned state | All platform curricula shown regardless of subject/grade labels. Not pre-filtered. | P0 | ⬜ Untested
AD-STD-04 | School Setup — Standard Sets | Search filters by name | Library visible | 1. Type 'NYSED' in search input | Only curricula with 'NYSED' in name shown. | P0 | ⬜ Untested
AD-STD-05 | School Setup — Standard Sets | Search filters by subject label | Library visible | 1. Type 'english' in search (case-insensitive) | Only curricula with subject_label containing 'english' shown. | P0 | ⬜ Untested
AD-STD-06 | School Setup — Standard Sets | Search filters by grade label | Library visible | 1. Type 'grade 6' in search | Only curricula with grade_label containing 'grade 6' shown. | P0 | ⬜ Untested
AD-STD-07 | School Setup — Standard Sets | Search no results | Library visible | 1. Type a string matching nothing | Shows 'No curricula match "..."' message. | P1 | ⬜ Untested
AD-STD-08 | School Setup — Standard Sets | Clear search restores list | Search has filtered results | 1. Clear the search input | Full platform library restored. | P1 | ⬜ Untested
AD-STD-09 | School Setup — Standard Sets | Assign curriculum | Library visible | 1. Click Assign on a curriculum | View switches to assigned state: curriculum name, standard count, Remove button. Standards table renders read-only. | P0 | ⬜ Untested
AD-STD-10 | School Setup — Standard Sets | Assigned standards table is read-only | Curriculum assigned | 1. View assigned curriculum | Standards table shows Code, Strand, Description. No delete or edit controls. | P1 | ⬜ Untested
AD-STD-11 | School Setup — Standard Sets | Remove assignment | Curriculum assigned | 1. Click Remove | Returns to unassigned state with library list visible. | P0 | ⬜ Untested
AD-STD-12 | School Setup — Standard Sets | Separate combos are independent | School has multiple subjects/grades | 1. Assign curriculum to English / Grade 6 2. Switch to Maths / Grade 6 | Maths / Grade 6 shows as unassigned independently. | P1 | ⬜ Untested
AD-STD-13 | School Setup — Standard Sets | create-standard-set API returns 410 | School admin token | 1. POST /api/admin/create-standard-set | Returns 410 Gone with message about platform admin route. | P1 | ⬜ Untested
AD-CLS-01 | School Setup — Class Assignments | View class assignments | On School Setup | 1. Class Assignments tab 2. Select subject + grade | Shows assigned teachers with Lead indicator. | P1 | ⬜ Untested
AD-CLS-02 | School Setup — Class Assignments | Assign teacher to class | Teachers exist, combo selected | 1. Select teacher from dropdown 2. Click Assign | Teacher appears in assignment list. | P1 | ⬜ Untested
AD-CLS-03 | School Setup — Class Assignments | Toggle lead teacher | Teacher assigned | 1. Click lead toggle on a teacher | Lead indicator updates. | P2 | ⬜ Untested
AD-CLS-04 | School Setup — Class Assignments | Remove class assignment | Teacher assigned | 1. Click remove on teacher | Teacher removed from assignment. | P2 | ⬜ Untested
AD-INI-01 | School Setup — Initiatives | Initiatives view accessible to admin | Admin logged in | 1. Look for Initiatives in admin sidebar 2. Click it | Initiatives nav item visible. Clicking loads the Initiatives view with "+ New Initiative" button. | P1 | ⬜ Untested
AD-INI-02 | School Setup — Initiatives | Admin creates initiative | Admin on Initiatives view | 1. Click "+ New Initiative" 2. Enter name: "Reading Initiative 2026" 3. Enter metric label: "% at grade level" 4. Set start date 5. Click "Create Initiative" | Initiative card appears with Active status, 0 participants, and the metric label shown. | P0 | ⬜ Untested
AD-INI-03 | School Setup — Initiatives | Initiative RLS — admin cannot see other schools' initiatives | Two schools each with an initiative | 1. Log in as admin of School B 2. Open Initiatives | Only School B's initiatives returned. School A's initiative not visible. | P1 | ⬜ Untested

## Teacher & HOD
Test Plan — Teacher / HOD ¦ Curriculum Tracker 2026–2027
Role: Teacher / HOD ¦ Total cases: 73 ¦ Generated: 2026-06-04
ID | Suite | Test Case | Preconditions | Steps | Expected Result | Priority | Status | Notes
TC-AUTH-01 | Authentication | Login as teacher | Account jade.teacher exists | 1. Enter username: jade.teacher 2. Enter password 3. Sign in | Lands on My Units page. Teacher sidebar visible. | P0 | ⬜ Untested
TC-AUTH-02 | Authentication | Teacher cannot access admin routes | Logged in as jade.teacher | 1. POST /api/admin/create-standard-set with teacher token | Returns 403 Forbidden | P1 | ⬜ Untested
TC-AUTH-03 | Authentication | Teacher cannot access platform routes | Logged in as jade.teacher | 1. GET /api/platform/list-schools with teacher token | Returns 403 Forbidden | P1 | ⬜ Untested
TC-STD-01 | Standards Loading | Standards load via school_curricula | School has curriculum assigned for teacher's subject/grade | 1. Log in as teacher 2. Navigate to Standards Coverage | Standards visible and grouped by strand. Loaded from school_curricula join, not old standard_sets.school_id. | P0 | ⬜ Untested
TC-STD-02 | Standards Loading | No standards if no curriculum assigned | School has NO curriculum assigned for this combo | 1. Log in as teacher with no assigned curriculum | Coverage view shows empty state. No standards listed. | P1 | ⬜ Untested
TC-STD-03 | Standards Loading | Standards scoped to school only | Two schools with different curricula | 1. Log in as teacher from School A | Only standards from School A's assigned curricula visible. School B standards not shown. | P0 | ⬜ Untested
TC-UNT-01 | My Units | My Units page loads | Teacher has assigned units | 1. Click My Units | List of assigned unit plans visible. | P1 | ⬜ Untested
TC-UNT-02 | My Units | Open unit plan | At least one unit assigned | 1. Click a unit title | Unit plan view opens with standards table, essential question, assessments. | P1 | ⬜ Untested
TC-LTP-01 | Long Term Plans | View master plans | LTP exists for teacher | 1. Click Master Plans | Teacher's LTPs listed with status badges. | P1 | ⬜ Untested
TC-LTP-02 | Long Term Plans | Create new unit | LTP exists | 1. Open LTP 2. Click Add Unit 3. Fill title, big idea, duration 4. Create | Unit created, navigates to UnitPlanView. | P1 | ⬜ Untested
TC-LTP-03 | Long Term Plans | Map standards to unit | Unit open in UnitPlanView, standards loaded | 1. Open Map Standards section 2. Select standards 3. Save | Standards appear in unit standards table sorted by strand. | P0 | ⬜ Untested
TC-LTP-04 | Long Term Plans | AI suggest standards | Unit with essential question, DeepSeek key set | 1. Open Map Standards 2. Click AI Suggest | 3–6 standards suggested based on unit theme. | P2 | ⬜ Untested
TC-LTP-05 | Long Term Plans | Submit unit for review | Unit has standards mapped | 1. Open unit 2. Click Submit for Review | Unit status changes to Submitted. HOD receives notification. | P0 | ⬜ Untested
TC-LTP-06 | Long Term Plans | Edit unit in Draft state | Unit in Draft status | 1. Open unit 2. Edit title 3. Save Changes | Changes persisted. | P1 | ⬜ Untested
TC-LTP-07 | Long Term Plans | Cannot edit Approved unit | Unit in Approved status | 1. Open approved unit | Fields read-only. Save Changes button not available. | P1 | ⬜ Untested
TC-COV-01 | Standards Coverage | Coverage view loads | Standards assigned via school_curricula | 1. Click Standards Coverage | Standards grouped by strand with coverage progress bars. | P1 | ⬜ Untested
TC-COV-02 | Standards Coverage | Coverage reflects mapped standards | Some standards mapped in LTP units | 1. Check coverage % vs units' mapped standards | Coverage percentage matches standards in approved/submitted units. | P1 | ⬜ Untested
TC-STU-01 | Student Progress | Student progress view loads | Students enrolled | 1. Click Student Progress | Students listed with attainment levels per standard. | P1 | ⬜ Untested
TC-HOD-01 | HOD — Review | HOD login — lands on Dashboard | Account hod.test exists | 1. Login as hod.test | HOD Dashboard loads with coverage heatmap by teacher × strand. | P0 | ⬜ Untested
TC-HOD-02 | HOD — Review | HOD coverage heatmap loads | Teachers have mapped standards via school_curricula | 1. View Dashboard | Heatmap shows teachers as rows, strands as columns, % values in cells. | P0 | ⬜ Untested
TC-HOD-03 | HOD — Review | Plan Reviews — submitted units appear | Teacher has submitted a unit | 1. Click Plan Reviews | Submitted units listed in FIFO order with teacher name and submission date. | P0 | ⬜ Untested
TC-HOD-04 | HOD — Review | Approve a unit | Unit in Submitted status | 1. Click Approve on a unit | Unit status changes to Approved. Teacher can no longer edit. | P0 | ⬜ Untested
TC-HOD-05 | HOD — Review | Request revision | Unit in Submitted status | 1. Click Revise 2. Enter feedback text 3. Submit | Unit status changes to Revision. Feedback visible to teacher. | P0 | ⬜ Untested
TC-HOD-06 | HOD — Review | Reject a unit | Unit in Submitted status | 1. Click Reject 2. Enter rejection reason 3. Confirm | Unit status changes to Rejected. Teacher must contact HOD to reopen. | P1 | ⬜ Untested
TC-HOD-07 | HOD — Review | HOD cannot review without feedback on revision | Revision modal open | 1. Open Revise modal 2. Leave feedback blank 3. Attempt submit | Submit button disabled until feedback entered. | P1 | ⬜ Untested
TC-HOD-08 | HOD — Review | Standards gap report shows per plan | Plan with missing standards | 1. On Plan Reviews, expand a plan | Gap report shows unmapped standards by strand. | P1 | ⬜ Untested
TC-REG-01 | Regression | Existing approved units retain standards | Units approved before architecture change | 1. Open any pre-existing approved unit | Standards still display correctly. No data loss from migration. | P0 | ⬜ Untested
TC-REG-02 | Regression | Delivery grid loads | HOD logged in | 1. Click Delivery Grid | Grid shows units across teachers and time. No errors. | P1 | ⬜ Untested
TC-REG-03 | Regression | Notifications load | Teacher logged in | 1. Check notification bell | Notifications appear (overdue, pending review, etc.). | P1 | ⬜ Untested
TC-ANA-01 | HOD — Analytics | Analytics view loads | HOD logged in, no student progress data | 1. Click Analytics in nav | Page loads. Ghost table skeleton shows strand column headers (Rdg Lit, Rdg Info, Writing, Speaking, Language) and 3 placeholder rows. Instruction text visible. Take Snapshot button hidden. | P1 | ⬜ Untested
TC-ANA-02 | HOD — Analytics | Take Snapshot hidden on empty grid | Analytics open, no student progress data | 1. Confirm no student progress data exists 2. Open Analytics view | "Take Snapshot" button is NOT visible in the page header. | P1 | ⬜ Untested
TC-ANA-03 | HOD — Analytics | Grid populates with student progress data | Students have attainment recorded | 1. Ensure student attainment records exist 2. Open Analytics | Strand attainment grid shows rows per class with % values per strand. Cells color-coded: ≥80% green, 40–79% amber, <40% red. Take Snapshot button appears. | P0 | ⬜ Untested
TC-ANA-04 | HOD — Analytics | Cell click opens attainment drill-down sheet | Grid has data | 1. Click any colored cell in the attainment grid | Sheet opens showing students in that class grouped by attainment level (Exceeding / Meeting / Approaching / Below / Not Assessed). | P1 | ⬜ Untested
TC-ANA-05 | HOD — Analytics | Take Snapshot saves + comparison panel appears | Grid populated, snapshot button visible | 1. Click "Take Snapshot" 2. Confirm toast/feedback 3. Click "Take Snapshot" again (second snapshot) | First snapshot: saved. Second snapshot: Benchmark Comparison panel appears below the grid with before/after bars per strand and ±pp delta labels. | P0 | ⬜ Untested
TC-ANA-06 | HOD — Analytics | Analytics scoped to active subject/grade context | HOD has multiple subject/grade assignments | 1. Switch context via sidebar context switcher to a different subject/grade 2. Open Analytics | Grid updates to show classes for the newly selected context only. | P2 | ⬜ Untested
TC-COA-01 | HOD — Coaching | Coaching view loads with teacher list | HOD logged in, teachers in school | 1. Click Coaching in nav | Two-panel view renders. Left panel lists all dept teachers with observation counts. Right panel shows first teacher's detail with tabs: Observations / Cycle / Mentoring / PD Log. | P0 | ⬜ Untested
TC-COA-02 | HOD — Coaching | Select teacher updates detail panel | Coaching view open | 1. Click a different teacher in the left panel | Right panel updates to the selected teacher's name and their observation/cycle data. | P1 | ⬜ Untested
TC-COA-03 | HOD — Coaching | Log Observation — inline form opens | Coaching view, teacher selected, Observations tab active | 1. Click "+ Log Observation" | Inline form expands (not a modal) with Date, Focus Area select, Observation notes textarea, Agreed next steps textarea, Save + Cancel buttons. | P1 | ⬜ Untested
TC-COA-04 | HOD — Coaching | Save observation persists and appears as card | Form open with all fields filled | 1. Set date to today 2. Select Focus Area: Literacy 3. Enter observation notes 4. Enter next steps 5. Click "Save Observation" | Form closes. Observation card appears with Literacy focus badge, date showing "Today", observation notes visible. Teacher counter in left panel increments to 1. | P0 | ⬜ Untested
TC-COA-05 | HOD — Coaching | Observation card expand/collapse shows next steps | At least one saved observation | 1. Click "Expand" on an observation card 2. Click "Collapse" | Expand: "Agreed next steps" label and text visible below a divider. Collapse: only focus badge, date, and note preview visible. | P1 | ⬜ Untested
TC-COA-06 | HOD — Coaching | Open Coaching Cycle creates 4-step tracker | Cycle tab active, no active cycle | 1. Click "Cycle" tab 2. Click "Open Cycle" | Cycle tracker appears with 4 steps: Observe → Debrief → Model → Reflect. Step 1 (Observe) highlighted as active. "Complete: Observe" button visible. | P1 | ⬜ Untested
TC-COA-07 | HOD — Coaching | Complete cycle step advances tracker | Active cycle at Step 1 | 1. Click "Complete: Observe" | Observe step shows green checkmark. Debrief becomes active step. Button updates to "Complete: Debrief". | P1 | ⬜ Untested
TC-COA-08 | HOD — Coaching | All 4 steps complete closes cycle | Cycle active, 3 steps already complete | 1. Click "Complete: Reflect" (final step) | All steps show green checkmarks. "Cycle complete" label visible. "New Cycle" button appears. Teacher in left panel no longer shows an active cycle step. | P1 | ⬜ Untested
TC-COA-09 | HOD — Coaching | Create mentoring pair | Mentoring tab, 2+ teachers in school | 1. Click "Assign Pair" 2. Select partner teacher, set role, choose cadence: Fortnightly 3. Click "Save Pair" | Pair card appears showing teacher names, Fortnightly cadence, "Never" as last check-in. | P2 | ⬜ Untested
TC-COA-10 | HOD — Coaching | Update check-in on mentoring pair | Mentoring pair exists | 1. Click "Update Check-in" on pair card | last_checkin_at updates. Card displays "Today" as last check-in. | P2 | ⬜ Untested
TC-COA-11 | HOD — Coaching | Add PD entry | PD Log tab open | 1. Click "+ Add Entry" 2. Select Type: Workshop 3. Enter date and focus area 4. Click "Save Entry" | Entry appears in PD log table with correct date, type, and focus area. | P2 | ⬜ Untested
TC-INT-01 | Interventions | Interventions tab visible on Student Progress | Logged in as teacher or HOD | 1. Navigate to Student Progress | "Progress" and "Interventions" tab buttons visible at the top of the view. | P1 | ⬜ Untested
TC-INT-02 | Interventions | New Intervention form validation | Interventions tab, teacher view | 1. Click "New Intervention" 2. Leave students, strands, and strategy empty 3. Attempt click "Create Intervention" | "Create Intervention" button remains disabled until students (1+), strands (1+), and strategy name are all provided. | P1 | ⬜ Untested
TC-INT-03 | Interventions | Create intervention saves as Active | Form filled with students, strand, strategy | 1. Select 2 students 2. Check Writing strand 3. Enter strategy: "Close reading circles" 4. Click "Create Intervention" | Intervention card appears with status badge "Active" (green), Writing strand badge, "2 students" label, strategy name, start date. | P0 | ⬜ Untested
TC-INT-04 | Interventions | Intervention card opens detail sheet | Active intervention exists | 1. Click an intervention card | Sheet opens showing student name list, outcome notes textarea (editable), "Move to Monitoring" and "Mark Concluded" buttons. | P1 | ⬜ Untested
TC-INT-05 | Interventions | Mark intervention Monitoring | Active intervention, detail sheet open | 1. Click "Move to Monitoring" | Status badge changes to "Monitoring" (amber). Sheet closes. Card reflects new status. | P1 | ⬜ Untested
TC-INT-06 | Interventions | Mark intervention Concluded with outcome notes | Detail sheet open | 1. Enter outcome notes in textarea 2. Click "Mark Concluded" | Status changes to "Concluded" (grey). Outcome notes saved. End date recorded. Card moves to collapsed "Concluded" section. | P0 | ⬜ Untested
TC-INT-07 | Interventions | Concluded section is collapsible | At least one concluded intervention | 1. Open Interventions tab 2. Look for collapsed "Concluded (N)" section 3. Click to expand | Section expands to show concluded intervention cards. Collapse hides them. | P1 | ⬜ Untested
TC-INT-08 | Interventions | HOD sees all dept interventions | Logged in as HOD, multiple teachers have interventions | 1. Navigate to Student Progress → Interventions tab as HOD | All teachers' active interventions visible, grouped under each teacher's name subheading. Filter bar (teacher, strand, status) visible. | P1 | ⬜ Untested
TC-INT-09 | Interventions | HOD filter by teacher | HOD, interventions from 2+ teachers | 1. Select a specific teacher in the teacher filter dropdown | Only that teacher's interventions displayed. Other teachers' cards hidden. | P2 | ⬜ Untested
TC-INT-10 | Interventions | HOD filter by strand | HOD, interventions targeting different strands | 1. Select Writing in the strand filter dropdown | Only interventions with Writing in their strand_codes shown. | P2 | ⬜ Untested
TC-DEP-01 | Department Collaboration | Department view loads for HOD | Logged in as HOD | 1. Click Department in nav | View loads with "MEETING NOTES" section (with top border separator), "Recognise" (outline) and "+ Meeting Note" (primary) buttons in header. Empty state shows chat icon and message. | P0 | ⬜ Untested
TC-DEP-02 | Department Collaboration | Department view is read-only for teacher | Logged in as teacher | 1. Click Department in nav | View loads showing meeting notes teacher attended and their action items. No "+ Meeting Note" or "Recognise" buttons visible. | P1 | ⬜ Untested
TC-DEP-03 | Department Collaboration | New Meeting Note form opens inline | HOD on Department view | 1. Click "+ Meeting Note" | Inline form expands (no modal) with date picker, attendees multi-select (dept teachers), agenda textarea, notes textarea, Add Action Item control. | P1 | ⬜ Untested
TC-DEP-04 | Department Collaboration | Save meeting note with action items persists | Inline form open and filled | 1. Set date, select attendees 2. Enter agenda and notes 3. Click "+ Action Item" → fill description, assignee, due date 4. Click "Save Meeting Note" | Note card appears in feed. Action item appears in "Pending Actions" section for HOD and the assigned teacher. | P0 | ⬜ Untested
TC-DEP-05 | Department Collaboration | Teacher sees meeting notes they attended | Teacher is in attendee_ids of a meeting note | 1. Log in as the teacher in attendance 2. Open Department | Meeting note visible in teacher's feed. HOD-only create buttons absent. | P1 | ⬜ Untested
TC-DEP-06 | Department Collaboration | Teacher can complete their own action item | Teacher has an assigned pending action item | 1. Teacher opens Department 2. Click checkbox on a Pending Action item | Checkbox updates. Item removed from Pending Actions list. | P1 | ⬜ Untested
TC-DEP-07 | Department Collaboration | HOD recognise a teacher | HOD on Department view | 1. Click "Recognise" 2. Select teacher from dropdown 3. Enter recognition note 4. Click "Send Recognition" | Gold recognition card appears in Recognitions section on HOD's view. Same card visible on that teacher's Department view. | P1 | ⬜ Untested
TC-DEP-08 | Department Collaboration | Teacher sees only their own recognitions | Teacher on Department, multiple teachers have recognitions | 1. Log in as teacher 2. Open Department → My Recognitions section | Only recognitions addressed to this teacher visible. Other teachers' recognitions not returned. | P0 | ⬜ Untested
TC-DEP-09 | Department Collaboration | Action items persist on page reload | Meeting note with action items saved | 1. Create meeting note with 2 action items 2. Reload page | Pending action items still listed. Meeting note still visible in feed. | P1 | ⬜ Untested
TC-DEP-10 | Department Collaboration | Department data isolated by school (RLS) | Two separate schools | 1. Log in as HOD of School A, create a meeting note 2. Log in as HOD of School B → open Department | School B HOD cannot see School A's meeting notes or action items. | P2 | ⬜ Untested
TC-INI-01 | Initiatives | HOD sees contextual guidance on empty initiatives | HOD logged in, no initiatives created by admin | 1. Click Initiatives in nav | Empty state shows: "No initiatives have been set up yet. Ask your school admin to create one — you'll be able to join and log progress here." | P1 | ⬜ Untested
TC-INI-02 | Initiatives | HOD joins initiative | Active initiative exists in school | 1. Click initiative card 2. In detail sheet, click "Join Initiative" | HOD added to participants list. Participant count on card increments. | P1 | ⬜ Untested
TC-INI-03 | Initiatives | HOD adds progress entry | HOD is participant, initiative is active | 1. Open initiative detail 2. Enter metric value in Add Progress Entry 3. Click "Add" | Progress entry appears in table with today's date and entered value. | P1 | ⬜ Untested
TC-INI-04 | Initiatives | HOD leaves initiative | HOD is a participant | 1. Open initiative detail 2. Click "Leave" | HOD removed from participants list. Participant count decrements. | P2 | ⬜ Untested
TC-INI-05 | Initiatives | Initiative scoped to school (RLS) | Two schools, initiative exists in School A | 1. Log in as HOD of School B 2. Open Initiatives | School A's initiative not visible to School B HOD. | P2 | ⬜ Untested
TC-REG-04 | Regression | Leadership nav does not break existing HOD views | HOD logged in | 1. Click through Dashboard, Master Plans, Delivery Grid, Plan Reviews, Standards Coverage 2. Click through Analytics, Coaching, Department, Initiatives | All 9 HOD nav items accessible. Existing views load without errors. "LEADERSHIP" section label visible in sidebar. | P0 | ⬜ Untested
TC-REG-05 | Regression | Interventions tab does not break existing Student Progress | Teacher logged in | 1. Open Student Progress 2. Verify Progress tab shows existing data 3. Switch to Interventions tab and back | Progress tab shows existing attainment data unchanged. Switching tabs causes no errors or data loss. | P1 | ⬜ Untested